## Sprint Backlog
Task ID | Sprint | Task | Description | Priority | Deliverable | Acceptance Criteria
S0-01 | Sprint 0 | Study airline business problem | Understand the ABC Airways business problem, objectives and data ecosystem. | High | Business Understanding | Business problem and project objective are clearly documented.
S0-02 | Sprint 0 | Identify stakeholders | Identify relevant business and project stakeholders and their needs. | High | Stakeholder List | Stakeholders and their requirements are documented.
S0-03 | Sprint 0 | Identify airline data sources | Identify and map the 10 project datasets to their corresponding airline source systems. | High | Source Identification | All 10 datasets are mapped to source systems.
S0-04 | Sprint 0 | Define project scope | Define what is included and excluded from the Enterprise Aviation Data Platform project. | High | Project Scope | In-scope and out-of-scope activities are documented.
S0-05 | Sprint 0 | Prepare Project Charter | Document project background, objectives, scope, stakeholders, technology, risks and success criteria. | High | Project Charter | Project Charter is complete and aligned with the project.
S0-06 | Sprint 0 | Prepare BRD | Document business objectives, stakeholder requirements, functional requirements and non-functional requirements. | High | BRD | Business requirements are documented and traceable.
S0-07 | Sprint 0 | Design Solution Architecture | Design the high-level architecture for the source systems, Pentaho, PostgreSQL staging and Git/GitHub. | High | Solution Architecture | Architecture clearly shows the Sprint 0/Sprint 1 data flow.
S0-08 | Sprint 0 | Prepare Product Backlog | Identify and prioritize the major activities planned for the overall project. | High | Product Backlog | Project work items are listed and prioritized.
S0-09 | Sprint 0 | Create GitHub repository | Create the shared Git/GitHub repository for project collaboration and version control. | High | Git Repository | Repository is created and accessible to the team.
S0-10 | Sprint 0 | Create repository structure | Create folders for documentation, Pentaho, SQL, datasets/sample data and project artifacts. | Medium | Repository Structure | Repository contains an organized project structure.
S1-01 | Sprint 1 | Prepare Source Inventory | Document each source system/dataset, format, record count, key fields and business purpose. | High | Source Inventory | All 10 datasets are recorded with required source details.
S1-02 | Sprint 1 | Prepare Data Dictionary | Document field names, data types, descriptions, source information and relevant validation notes. | High | Data Dictionary | Data dictionary covers the required source fields.
S1-03 | Sprint 1 | Develop Pentaho ETL pipelines | Create Pentaho transformations/jobs to read the source datasets and load PostgreSQL staging. | High | Pentaho ETL Pipelines | Pipelines execute successfully for the intended source datasets.
S1-04 | Sprint 1 | Configure source ingestion | Configure appropriate Pentaho input steps for CSV, Excel and JSON datasets and map fields to staging. | High | Ingestion Configuration | Source files are read and mapped to intended staging structures.
S1-05 | Sprint 1 | Create PostgreSQL staging database | Create source-aligned staging tables for the ingested aviation datasets. | High | PostgreSQL Staging Database | Staging tables are created and ready for source data.
S1-06 | Sprint 1 | Load data into staging | Run ETL pipelines and load successfully processed records into PostgreSQL staging tables. | High | Loaded Staging Data | Expected source records are loaded and record counts can be verified.
S1-07 | Sprint 1 | Implement logging and exception handling | Capture pipeline execution information, errors, rejected records and processing counts. | High | Logging & Exception Handling | ETL failures and rejections are captured and traceable.
S1-08 | Sprint 1 | Maintain Git commit history | Commit ETL files, SQL scripts, documentation and Sprint 1 changes to Git/GitHub. | Medium | Git Commit History | Sprint 1 changes are traceable through meaningful Git commits.
S1-09 | Sprint 1 | Validate Sprint 1 outputs | Review Source Inventory, Data Dictionary, ETL pipelines, staging database and logs against Sprint 1 requirements. | Medium | Sprint 1 Validation | Sprint 1 deliverables are complete and consistent.