## Sprint Backlog
Task ID | Sprint | Task | Description | Priority | Owner | Status | Deliverable | Acceptance Criteria
S0-01 | Sprint 0 | Study airline business problem | Understand ABC Airways business problem, objectives and data ecosystem. | High | Member 1 | To Do | Business Understanding | Team can clearly explain the business problem and project objective.
S0-02 | Sprint 0 | Identify stakeholders | Identify Flight Operations, Airport Operations, Customer Service, Maintenance, Commercial and Executive Management stakeholders. | High | Member 2 | To Do | Stakeholder List | Stakeholders and their business needs are documented.
S0-03 | Sprint 0 | Identify airline data sources | Map the 10 project datasets to the corresponding airline source systems. | High | Member 1 | To Do | Source Identification | All 10 datasets are mapped to source systems.
S0-04 | Sprint 0 | Define project scope | Define the activities and boundaries of the Enterprise Aviation Data Platform. | High | Member 3 | To Do | Project Scope | In-scope and out-of-scope activities are documented.
S0-05 | Sprint 0 | Prepare Project Charter | Document project background, objectives, scope, stakeholders, technology, risks and success criteria. | High | Member 3 | To Do | Project Charter | Project Charter is completed and aligned with the project statement.
S0-06 | Sprint 0 | Prepare BRD | Document business objectives, stakeholder requirements, functional requirements and non-functional requirements. | High | Member 3 | To Do | BRD | Business requirements are documented and traceable to project objectives.
S0-07 | Sprint 0 | Design Solution Architecture | Design the high-level architecture showing data sources, Pentaho, PostgreSQL, Python/Pandas, warehouse and Power BI. | High | Member 2 | To Do | Solution Architecture | Architecture clearly shows the end-to-end data flow and technologies.
S0-08 | Sprint 0 | Prepare Product Backlog | Identify and prioritize the major activities planned for the project. | High | Member 1 | To Do | Product Backlog | Project work items are listed and prioritized.
S0-09 | Sprint 0 | Create GitHub repository | Create the shared Git/GitHub repository for collaborative project development. | High | Member 1 | To Do | Git Repository | All three team members can access the repository.
S0-10 | Sprint 0 | Create enterprise repository structure | Create folders for documentation, Pentaho, Python, SQL, data samples and Power BI. | Medium | Member 2 | To Do | Repository Structure | Repository contains a clear and organized project structure.