## Product Backlog
ENTERPRISE AVIATION DATA PLATFORM (EADP)
UC8 — Product Backlog ¦ Agile Scrum ¦ Sprint 0–3
Backlog ID | Epic | User Story / Requirement | Description | Priority | Sprint | Story Points | Acceptance Criteria | Dependency | Status | Owner
PB-001 | Project Initiation | Study airline business problem | Understand ABC Airways operational and analytics challenges. | High | Sprint 0 | 3 | Business problem, objectives, challenges and outcomes documented. | None | Completed
PB-002 | Project Initiation | Identify business stakeholders | Identify Flight Operations, Airport Operations, Customer Service, Maintenance, Commercial and Executive Management stakeholders. | High | Sprint 0 | 2 | All six stakeholder groups documented with responsibilities. | PB-001 | Completed
PB-003 | Project Initiation | Define project objectives | Document objectives for an enterprise-grade aviation data platform. | High | Sprint 0 | 2 | Objectives cover heterogeneous ingestion, quality, warehouse, governance, analytics and Git. | PB-001 | Completed
PB-004 | Project Initiation | Define project scope | Define in-scope and out-of-scope project boundaries. | High | Sprint 0 | 3 | Scope is documented and approved for sprint planning. | PB-003 | Completed
PB-005 | Project Initiation | Prepare Business Requirements Document | Document business requirements for the EADP project. | High | Sprint 0 | 5 | BRD exists and reflects the project business problem, objectives, stakeholders and scope. | PB-001; PB-002; PB-004 | Completed
PB-006 | Project Initiation | Create project charter | Document project purpose, scope, stakeholders, milestones and governance. | High | Sprint 0 | 3 | Project charter is available in docs. | PB-004 | Completed
PB-007 | Project Initiation | Prepare Product Backlog | Create prioritized backlog covering project work across all sprints. | High | Sprint 0 | 3 | Backlog has IDs, priorities, sprints, estimates, acceptance criteria and status. | PB-005; PB-006 | In Progress
PB-008 | Architecture & Repository | Design enterprise data architecture | Define the end-to-end data platform architecture. | High | Sprint 0 | 5 | Architecture shows source systems, ETL, landing/staging, curated, warehouse and analytics layers. | PB-004 | Completed
PB-009 | Architecture & Repository | Design high-level architecture diagram | Create architecture diagram for the EADP platform. | High | Sprint 0 | 5 | Architecture diagram is available and version controlled. | PB-008 | Completed
PB-010 | Architecture & Repository | Create Git repository | Initialize local repository and connect it to GitHub. | High | Sprint 0 | 2 | Repository is initialized, remote configured and main branch pushed. | PB-004 | Completed
PB-011 | Architecture & Repository | Create enterprise repository structure | Create docs, datasets, bronze, silver, gold, pentaho, python, sql, metadata, lineage, dashboards, deployment and tests directories. | High | Sprint 0 | 3 | Required directory structure exists in repository. | PB-010 | Completed
PB-012 | Architecture & Repository | Define Git commit convention | Define meaningful conventional commit prefixes for project history. | Medium | Sprint 0 | 2 | Commit convention documented and followed. | PB-010 | Completed
PB-013 | Architecture & Repository | Define sprint milestone tagging strategy | Define sprint-0, sprint-1 and final-release tags. | Medium | Sprint 0 | 2 | Tagging strategy documented and used at sprint milestones. | PB-010 | Not Started
PB-014 | Source Discovery | Identify Flight Operations data source | Catalog Flight Operations source data. | High | Sprint 1 | 2 | Source, format, entity, owner, ingestion method and target are recorded. | PB-007 | Completed
PB-015 | Source Discovery | Identify Passenger Reservation data source | Catalog Passenger Reservation System source data. | High | Sprint 1 | 2 | Source, format, entity, owner, ingestion method and target are recorded. | PB-007 | Completed
PB-016 | Source Discovery | Identify Airport Operations data source | Catalog Airport Operations source data. | High | Sprint 1 | 2 | Source, format, entity, owner, ingestion method and target are recorded. | PB-007 | Completed
PB-017 | Source Discovery | Identify Baggage Handling data source | Catalog Baggage Handling source data. | High | Sprint 1 | 2 | Source, format, entity, owner, ingestion method and target are recorded. | PB-007 | Completed
PB-018 | Source Discovery | Identify Aircraft Maintenance data source | Catalog Aircraft Maintenance source data. | High | Sprint 1 | 2 | Source, format, entity, owner, ingestion method and target are recorded. | PB-007 | Completed
PB-019 | Source Discovery | Identify Crew Scheduling data source | Catalog Crew Scheduling source data. | High | Sprint 1 | 2 | Source, format, entity, owner, ingestion method and target are recorded. | PB-007 | Completed
PB-020 | Source Discovery | Identify Ticketing and Booking data source | Catalog Ticketing and Booking source data. | High | Sprint 1 | 2 | Source, format, entity, owner, ingestion method and target are recorded. | PB-007 | Completed
PB-021 | Source Discovery | Identify CRM data source | Catalog CRM source data. | High | Sprint 1 | 2 | Source, format, entity, owner, ingestion method and target are recorded. | PB-007 | Completed
PB-022 | Source Discovery | Identify Flight Delay data source | Catalog Flight Delay source data. | High | Sprint 1 | 2 | Source, format, entity, owner, ingestion method and target are recorded. | PB-007 | Completed
PB-023 | Source Discovery | Identify Aircraft IoT data source | Catalog Aircraft IoT source data. | High | Sprint 1 | 2 | Source, format, entity, owner, ingestion method and target are recorded. | PB-007 | Completed
PB-024 | Source Discovery | Prepare Source Inventory | Create a consolidated source inventory for all identified airline systems. | High | Sprint 1 | 5 | All identified sources include format, business area, ingestion method, target layer/table and ownership. | PB-014; PB-015; PB-016; PB-017; PB-018; PB-019; PB-020; PB-021; PB-022; PB-023 | Not Started
PB-025 | Source Discovery | Prepare Data Dictionary | Define source fields, types, business definitions, nullability, keys, targets and transformation rules. | High | Sprint 1 | 5 | Dictionary covers source and target fields for ingested datasets. | PB-024 | Not Started
PB-026 | Data Ingestion | Design ingestion framework | Define common ingestion pattern for CSV, Excel, JSON, XML and SQL sources. | High | Sprint 1 | 3 | Framework defines extract, validate, transform, load, logging and exception handling. | PB-024; PB-025 | Not Started
PB-027 | Data Ingestion | Implement CSV ingestion | Build Pentaho transformations for CSV datasets. | High | Sprint 1 | 5 | CSV sources load successfully into PostgreSQL staging with mapping and validation. | PB-026 | Not Started
PB-028 | Data Ingestion | Implement Excel ingestion | Build Pentaho transformations for Excel datasets. | High | Sprint 1 | 5 | Excel sources load successfully into PostgreSQL staging with mapping and validation. | PB-026 | Not Started
PB-029 | Data Ingestion | Implement JSON ingestion | Build Pentaho transformations for JSON datasets. | High | Sprint 1 | 5 | JSON sources load successfully into PostgreSQL staging with mapping and validation. | PB-026 | Not Started
PB-030 | Data Ingestion | Implement XML ingestion | Build Pentaho transformations for XML data. | High | Sprint 1 | 5 | XML source loads successfully into PostgreSQL staging with mapping and validation. | PB-026 | Not Started
PB-031 | Data Ingestion | Implement SQL ingestion | Build Pentaho transformation for SQL/relational source data. | High | Sprint 1 | 5 | SQL source is extracted and loaded into PostgreSQL staging with validation. | PB-026 | Not Started
PB-032 | Data Ingestion | Implement PostgreSQL staging tables | Create staging schema and source-aligned staging tables. | High | Sprint 1 | 5 | Staging tables exist with correct data types, keys where applicable and audit columns as designed. | PB-025 | Not Started
PB-033 | Data Ingestion | Implement ingestion logging | Capture pipeline start/end, source, records read, loaded, rejected, errors and status. | High | Sprint 1 | 3 | Successful and failed pipeline executions generate useful operational logs. | PB-026 | Not Started
PB-034 | Data Ingestion | Implement exception handling | Handle invalid records and pipeline failures without silently losing errors. | High | Sprint 1 | 3 | Exceptions are captured, rejected records are traceable and pipeline status is visible. | PB-026 | Not Started
PB-035 | Data Ingestion | Validate ingested records | Perform row count, null, duplicate, datatype and key validation after ingestion. | High | Sprint 1 | 5 | Validation checks pass or failures are documented and traceable. | PB-027; PB-028; PB-029; PB-030; PB-031; PB-032 | Not Started
PB-036 | Data Profiling & Quality | Profile aviation datasets using Python/Pandas | Generate structural and statistical profiles of source/staging datasets. | High | Sprint 2 | 5 | Profiles include schema, missingness, distributions and basic quality indicators. | PB-035 | Not Started
PB-037 | Data Profiling & Quality | Analyze missing values | Identify and report missing values in critical fields. | High | Sprint 2 | 3 | Missingness is quantified by dataset and critical field. | PB-036 | Not Started
PB-038 | Data Profiling & Quality | Identify duplicate passenger records | Detect duplicate passenger records and document rules. | High | Sprint 2 | 3 | Duplicate candidates are identified and remediation rules documented. | PB-036 | Not Started
PB-039 | Data Profiling & Quality | Identify flight data inconsistencies | Detect invalid or inconsistent flight information. | High | Sprint 2 | 3 | Flight quality exceptions are identified and documented. | PB-036 | Not Started
PB-040 | Data Profiling & Quality | Analyze baggage data quality | Profile baggage records for missing, duplicate and inconsistent values. | Medium | Sprint 2 | 3 | Baggage quality findings are documented. | PB-036 | Not Started
PB-041 | Data Profiling & Quality | Analyze aircraft maintenance data quality | Profile maintenance records for data quality issues. | High | Sprint 2 | 3 | Maintenance quality findings are documented. | PB-036 | Not Started
PB-042 | Data Profiling & Quality | Standardize master data | Standardize passenger, airport, aircraft and flight master data. | High | Sprint 2 | 5 | Standardization rules are applied consistently and exceptions are tracked. | PB-037; PB-038; PB-039; PB-041 | Not Started
PB-043 | Data Profiling & Quality | Create data quality report | Summarize profiling results, issues, rules and remediation status. | High | Sprint 2 | 5 | Report includes quality dimensions, findings and recommended actions. | PB-036; PB-037; PB-038; PB-039; PB-040; PB-041 | Not Started
PB-044 | Data Warehouse | Design dimensional model | Design star schema for aviation analytics. | High | Sprint 2 | 5 | Fact and dimension relationships support required operational analytics. | PB-042 | Not Started
PB-045 | Data Warehouse | Design fact tables | Define measurable business events and grain for fact tables. | High | Sprint 2 | 5 | Fact table grains, measures and foreign keys are documented. | PB-044 | Not Started
PB-046 | Data Warehouse | Design dimension tables | Define passenger, airport, aircraft, flight and other required dimensions. | High | Sprint 2 | 5 | Dimension attributes, keys and relationships are documented. | PB-044 | Not Started
PB-047 | Data Warehouse | Create PostgreSQL warehouse schema | Implement warehouse schemas and tables in PostgreSQL. | High | Sprint 2 | 5 | Warehouse objects are created successfully in PostgreSQL. | PB-045; PB-046 | Not Started
PB-048 | Data Warehouse | Load dimension tables | Populate curated dimension tables. | High | Sprint 2 | 5 | Dimensions load successfully with valid keys and standardized attributes. | PB-047 | Not Started
PB-049 | Data Warehouse | Load fact tables | Populate aviation fact tables from curated data. | High | Sprint 2 | 5 | Facts load at the defined grain and pass referential checks. | PB-047; PB-048 | Not Started
PB-050 | Data Warehouse | Implement warehouse validation | Validate row counts, referential integrity and business rules. | High | Sprint 2 | 3 | Warehouse validation results are documented. | PB-048; PB-049 | Not Started
PB-051 | Data Warehouse | Create operational SQL queries | Develop SQL queries for operational reporting. | Medium | Sprint 2 | 3 | Queries return validated KPIs and operational insights. | PB-049 | Not Started
PB-052 | Governance & Lineage | Create metadata repository | Maintain technical and business metadata for platform assets. | High | Sprint 3 | 5 | Metadata repository captures source, target, ownership and transformation information. | PB-025; PB-047 | Not Started
PB-053 | Governance & Lineage | Create business glossary | Define common aviation business terms and KPI terminology. | Medium | Sprint 3 | 3 | Business terms have clear definitions and ownership. | PB-052 | Not Started
PB-054 | Governance & Lineage | Create source-to-target mapping | Document field-level mappings and transformation rules. | High | Sprint 3 | 5 | Mappings cover source, staging, curated and warehouse targets. | PB-025; PB-047 | Not Started
PB-055 | Governance & Lineage | Document data lineage | Document end-to-end source-to-analytics lineage. | High | Sprint 3 | 5 | Lineage identifies movement and transformations from source to reporting. | PB-054 | Not Started
PB-056 | Governance & Lineage | Implement data reconciliation | Reconcile passenger, baggage, flight and maintenance data across layers. | High | Sprint 3 | 5 | Reconciliation checks are executed and exceptions documented. | PB-050; PB-055 | Not Started
PB-057 | Governance & Lineage | Document data quality rules | Document validation and quality rules used across the platform. | Medium | Sprint 3 | 3 | Rules are traceable to datasets and validation processes. | PB-043 | Not Started
PB-058 | ETL Orchestration | Create Pentaho transformation structure | Organize .ktr transformations by source and purpose. | High | Sprint 1 | 3 | Transformation directory is organized and naming convention is followed. | PB-026 | Not Started
PB-059 | ETL Orchestration | Create Pentaho job workflows | Orchestrate transformations using Pentaho jobs. | High | Sprint 3 | 5 | Jobs execute required dependencies in the correct sequence. | PB-033; PB-034 | Not Started
PB-060 | ETL Orchestration | Implement job-level logging | Capture execution status and operational metrics for jobs. | High | Sprint 3 | 3 | Job runs provide traceable execution logs. | PB-059 | Not Started
PB-061 | ETL Orchestration | Implement failure handling | Implement job-level failure and recovery handling. | High | Sprint 3 | 3 | Failures are detected, logged and routed for investigation. | PB-059; PB-060 | Not Started
PB-062 | ETL Orchestration | Test complete ETL workflow | Perform end-to-end ETL integration testing. | High | Sprint 3 | 5 | Complete workflow executes successfully and validation results are documented. | PB-059; PB-061 | Not Started
PB-063 | Analytics & Dashboards | Define aviation KPIs | Define KPIs for flight, passenger, maintenance, baggage and executive analytics. | High | Sprint 3 | 3 | KPI definitions, formulas, dimensions and data sources are documented. | PB-051; PB-053 | Not Started
PB-064 | Analytics & Dashboards | Create flight operations dashboard | Develop dashboard for flight punctuality and delay trends. | High | Sprint 3 | 5 | Dashboard supports flight punctuality and delay analysis. | PB-063 | Not Started
PB-065 | Analytics & Dashboards | Create passenger analytics dashboard | Develop dashboard for passenger booking and travel patterns. | High | Sprint 3 | 5 | Dashboard supports passenger booking/travel analysis. | PB-063 | Not Started
PB-066 | Analytics & Dashboards | Create aircraft and maintenance dashboard | Develop dashboard for aircraft utilization and maintenance schedules. | High | Sprint 3 | 5 | Dashboard supports utilization and maintenance monitoring. | PB-063 | Not Started
PB-067 | Analytics & Dashboards | Create baggage analytics dashboard | Develop dashboard for baggage handling performance. | Medium | Sprint 3 | 5 | Dashboard supports baggage performance analysis. | PB-063 | Not Started
PB-068 | Analytics & Dashboards | Create executive dashboard | Develop executive operational and financial reporting dashboard. | High | Sprint 3 | 5 | Dashboard provides executive-level operational and financial insights. | PB-063 | Not Started
PB-069 | Analytics & Dashboards | Validate dashboard metrics | Reconcile dashboard KPIs to trusted warehouse queries. | High | Sprint 3 | 3 | Dashboard metrics match validated source/warehouse calculations. | PB-064; PB-065; PB-066; PB-067; PB-068 | Not Started
PB-070 | Testing & Documentation | Create ingestion test cases | Document test cases for source ingestion pipelines. | High | Sprint 1 | 3 | Test cases cover successful, invalid and exception scenarios. | PB-035 | Not Started
PB-071 | Testing & Documentation | Create data quality test cases | Document test cases for profiling and quality rules. | High | Sprint 2 | 3 | Test cases cover missing, duplicate, consistency and validity checks. | PB-043 | Not Started
PB-072 | Testing & Documentation | Perform integration testing | Test interaction between ingestion, staging, curated and warehouse components. | High | Sprint 3 | 5 | Integration tests execute with documented results. | PB-050; PB-062 | Not Started
PB-073 | Testing & Documentation | Perform end-to-end testing | Validate the full source-to-dashboard workflow. | High | Sprint 3 | 5 | End-to-end flow passes critical acceptance tests. | PB-069; PB-072 | Not Started
PB-074 | Testing & Documentation | Prepare final technical documentation | Compile architecture, ETL, database, governance, testing and analytics documentation. | High | Sprint 3 | 5 | Final technical documentation is complete and version controlled. | PB-073 | Not Started
PB-075 | Testing & Documentation | Prepare final project presentation | Prepare final presentation of solution, results and learnings. | High | Sprint 3 | 3 | Presentation covers problem, architecture, implementation, analytics and outcomes. | PB-074 | Not Started
PB-076 | Testing & Documentation | Create final Git release | Tag and document final project release in Git. | High | Sprint 3 | 2 | Final release tag exists and repository history is complete. | PB-074; PB-075 | Not Started

## Dashboard
EADP PRODUCT BACKLOG DASHBOARD
Total Backlog Items |  |  |  |  | Status | Count
Completed |  |  |  |  | Completed
In Progress |  |  |  |  | In Progress
Not Started |  |  |  |  | Not Started
Blocked |  |  |  |  | Blocked
Total Story Points
Sprint | Items | Completed | Story Points | Completion %
Sprint 0
Sprint 1
Sprint 2
Sprint 3
Epic | Items | Completed | Story Points
Analytics & Dashboards
Architecture & Repository
Data Ingestion
Data Profiling & Quality
Data Warehouse
ETL Orchestration
Governance & Lineage
Project Initiation
Source Discovery
Testing & Documentation

## Instructions
EADP PRODUCT BACKLOG — INSTRUCTIONS
Purpose | This workbook is the EADP Product Backlog for UC8. It converts the source-defined sprint roadmap into trackable backlog items.
How to use | Use Product Backlog as the master list. Filter by Sprint, Epic, Priority or Status. Use Dashboard for summary.
Status tags | Completed = green; In Progress = yellow; Not Started = gray; Blocked = red.
Priority tags | High = red; Medium = orange; Low = gray.
Sprint tags | Sprint 0 = blue; Sprint 1 = orange; Sprint 2 = green; Sprint 3 = purple.
Story points | Relative effort estimate. These are planning estimates, not hours.
Acceptance criteria | Definition of Done for each backlog item. Update only when requirements or implementation decisions change.
Git history | Commit meaningful changes as work is completed; do not create artificial commits.
Source basis | The UC8 source defines Sprint 0 project initiation/architecture, Sprint 1 discovery/ingestion, Sprint 2 profiling/warehouse and Sprint 3 governance/lineage/analytics.

## Lists
Priority | Sprint | Status
High | Sprint 0 | Not Started
Medium | Sprint 1 | In Progress
Low | Sprint 2 | Completed
| Sprint 3 | Blocked